{"text_format":"1","workbook":"xlsx","n_sheets":4,"sheets":["Cover","CPM-Netzplan 1","CPM-Netzplan 2","CPM-Netzplan 3"],"not_rendered":{"charts":0,"images":1,"macros":1,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Cover","index":0,"n_rows":19,"n_cols":5,"rows_kept":19,"cut":false,"hidden":false,"merged":[]}
[]
[]
[]
[null,"Die Welt der VBA-Objekte"]
[]
[null,"Buchdaten"]
[null,"Kapitel","1 Grundlagen"]
[null,null,"1.5 Formen"]
[]
[null,"Inhalt"]
[null,"Module","modCreate","Code 1-52","CreateAll"]
[null,null,null,"Code 1-52","DeleteAll"]
[null,"Klassenmodule","clsKnoten","Code 1-48","Create "]
[null,null,"clsLine","Code 1-53","Create"]
[]
[null,"Bearbeitung"]
[null,"Version ","v1.0"]
[null,"Autor","Harald Nahrstedt"]
[null,"Letzte Bearbeitung","2016-01-17"]

{"sheet":"CPM-Netzplan 1","index":1,"n_rows":13,"n_cols":8,"rows_kept":13,"cut":false,"hidden":false,"merged":[[1,1,1,2]]}
[]
[null,"Aktivität"]
[null,"Nr","Bez.","von ","nach","D","FAZ","SAZ"]
[null,1,"Start",null,"2/3",0]
[null,2,"Materialbestellung",1,"4/5",3]
[null,3,"Arbeitsplanung",1,6,5]
[null,4,"Materialkosten",2,8,4]
[null,5,"Materiallieferung",2,9,7]
[null,6,"Personalschulung",3,9,4]
[null,7,"Lohnkosten",3,8,5]
[null,8,"Selbstkosten","4/7",10,5]
[null,9,"Fertigung","5/6",10,6]
[null,10,"Lieferung",9,null,1]

{"sheet":"CPM-Netzplan 2","index":2,"n_rows":13,"n_cols":8,"rows_kept":13,"cut":false,"hidden":false,"merged":[[1,1,1,2]]}
[]
[null,"Aktivität"]
[null,"Nr","Bez.","von ","nach","D","FAZ","SAZ"]
[null,1,"Start",null,"2/3",0,0,{"$f":"MIN(H6-F6,H5-F5)","v":0}]
[null,2,"Materialbestellung",1,"4/5",3,{"$f":"G4+F5","v":3},{"$f":"MIN(H8-F8,H7-F7)","v":3}]
[null,3,"Arbeitsplanung",1,6,5,{"$f":"G4+F6","v":5},{"$f":"MIN(H10-F10,H9-F9)","v":6}]
[null,4,"Materialkosten",2,8,4,{"$f":"G5+F7","v":7},{"$f":"H11-F11","v":11}]
[null,5,"Materiallieferung",2,9,7,{"$f":"G5+F8","v":10},{"$f":"H12-F12","v":10}]
[null,6,"Personalschulung",3,9,4,{"$f":"G6+F9","v":9},{"$f":"H12-F12","v":10}]
[null,7,"Lohnkosten",3,8,5,{"$f":"G6+F10","v":10},{"$f":"H11-F11","v":11}]
[null,8,"Selbstkosten","4/7",10,5,{"$f":"MAX(G7,G10)+F11","v":15},{"$f":"H12","v":16}]
[null,9,"Fertigung","5/6",10,6,{"$f":"MAX(G8,G9)+F12","v":16},{"$f":"G13-F13","v":16}]
[null,10,"Lieferung",9,null,1,{"$f":"MAX(G11,G12)+F13","v":17},17]

{"sheet":"CPM-Netzplan 3","index":3,"n_rows":13,"n_cols":8,"rows_kept":13,"cut":false,"hidden":false,"merged":[[1,1,1,2]]}
[]
[null,"Fertigung"]
[null,"Nr","Bez.","vor","nach","D","FAZ","SAZ"]
[null,1,"Start",null,"2/3",0]
[null,2,"Materiallieferung",1,"4/5",3]
[null,3,"Bauteil C",1,"6/7",5]
[null,4,"Bauteil A fräsen",2,8,4]
[null,5,"Bauteil B hobeln",2,9,7]
[null,6,"Bauteil C drehen",3,9,4]
[null,7,"Bauteil D bohren",3,10,5]
[null,8,"Bauteil A bohren",4,10,5]
[null,9,"Gruppe montieren","5/6",10,6]
[null,10,"Produkt montieren","7/8/9",null,1]