{"text_format":"1","workbook":"xlsx","n_sheets":2,"sheets":["Cover","CPM-Netzplan"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Cover","index":0,"n_rows":20,"n_cols":5,"rows_kept":20,"cut":false,"hidden":false,"merged":[]}
[]
[]
[]
[null,"Die Welt der VBA-Objekte"]
[]
[null,"Buchdaten"]
[null,"Kapitel","1 Grundlagen"]
[null,null,"1.5 Formen"]
[]
[null,"Inhalt"]
[null,"CodeContainer","modCreate","Codeliste 1-52","CreateAll"]
[]
[]
[null,"Bearbeitung"]
[null,"Version ","2.0"]
[null,"Autor","Harald Nahrstedt"]
[null,"Letzte Bearbeitung","2021-11-19"]
[]
[]
[null,"Springer Vieweg Verlag"]

{"sheet":"CPM-Netzplan","index":1,"n_rows":13,"n_cols":8,"rows_kept":13,"cut":false,"hidden":false,"merged":[[1,1,1,2]]}
[]
[null,"Fertigung"]
[null,"Nr","Bez.","vor","nach","D","FAZ","SAZ"]
[null,1,"Start",null,"2/3",0]
[null,2,"Materiallieferung",1,"4/5",3]
[null,3,"Bauteil C",1,"6/7",5]
[null,4,"Bauteil A fräsen",2,8,4]
[null,5,"Bauteil B hobeln",2,9,7]
[null,6,"Bauteil C drehen",3,9,4]
[null,7,"Bauteil D bohren",3,10,5]
[null,8,"Bauteil A bohren",4,10,5]
[null,9,"Gruppe montieren","5/6",10,6]
[null,10,"Produkt montieren","7/8/9",null,1]