{"text_format":"1","workbook":"xlsx","n_sheets":2,"sheets":["Cover","PSP IT-Projekt"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Cover","index":0,"n_rows":23,"n_cols":3,"rows_kept":23,"cut":false,"hidden":false,"merged":[]}
[]
[]
[null,"Excel + VBA "]
[null,"für Controller"]
[]
[]
[null,"Kapitel",10]
[null,"Thema","Strategisches Projekt-Controlling"]
[]
[null,"Inhalt","Projekt-Struktur-Plan"]
[null,null,"am Beispiel eines IT-Projekts"]
[null,null," "]
[]
[]
[]
[]
[]
[null,"Autor","Harald Nahrstedt"]
[null,"Datum","2019-01-01"]
[null,"Version","1.0"]
[]
[]
[null,"Springer Verlag"]

{"sheet":"PSP IT-Projekt","index":1,"n_rows":30,"n_cols":4,"rows_kept":30,"cut":false,"hidden":false,"merged":[]}
["Nr","Aufgabe","Status",{"$f":"AVERAGE(C5,C10,C14,C20,C25,C30)","v":0.38125000000000003}]
["1.1","Lastenheft",1]
["1.2","Pflichtenheft",1]
["1.3","Systementwurf",0.9]
["1","Konzeptentwicklung",{"$f":"SUM(C2:C4)/COUNT(C2:C4)","v":0.96666666666666667}]
["2.1","Modulentwicklung",0.2]
["2.2","Modul Berichte",0.35]
["2.3","Modul A",0.1]
["2.4","Systemintegration"]
["2","Programmierung",{"$f":"SUM(C6:C9)/COUNT(C6:C9)","v":0.21666666666666667}]
["3.1","Testplanung",0.7]
["3.2","Systemakzeptanztest",0.1]
["3.3","Reviews",0.15]
["3","Qualitätssicherung",{"$f":"SUM(C11:C13)/COUNT(C11:C13)","v":0.31666666666666665}]
["4.1","Arbeitsorganisation",0.35]
["4.2","Mitarbeiterschulung",0.25]
["4.3","Hardwarebestellung",0.3]
["4.4","Installation"]
["4.5","Abnahme"]
["4","Implementierung",{"$f":"SUM(C15:C19)/COUNT(C15:C19)","v":0.3}]
["5.1","Systembeschreibung",0.1]
["5.2","Testberichte",0.1]
["5.3","Benutzerhandbücher",0.55000000000000004]
["5.4","Konfigurationsmanagement",0.05]
["5","Dokumentation",{"$f":"SUM(C21:C24)/COUNT(C21:C24)","v":0.2}]
["6.1","Projektorganisation",0.6]
["6.2","Projektplanung",0.4]
["6.3","Projektsteuerung",0.1]
["6.4","Projektdokumentation",0.05]
["6","Projektmanagement",{"$f":"SUM(C26:C29)/COUNT(C26:C29)","v":0.28750000000000003}]