{"text_format":"1","workbook":"xlsx","n_sheets":2,"sheets":["Cover","RTA"],"not_rendered":{"charts":1,"images":0,"macros":1,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Cover","index":0,"n_rows":23,"n_cols":3,"rows_kept":23,"cut":false,"hidden":false,"merged":[]}
[]
[]
[null,"Excel + VBA "]
[null,"für Controller"]
[]
[]
[null,"Kapitel",11]
[null,"Thema","Operatives Projekt-Controlling"]
[]
[null,"Inhalt","Ressourcen-Trend-Analyse"]
[]
[null,null," "]
[]
[]
[]
[]
[]
[null,"Autor","Harald Nahrstedt"]
[null,"Datum","2019-01-01"]
[null,"Version","1.0"]
[]
[]
[null,"Springer Verlag"]

{"sheet":"RTA","index":1,"n_rows":8,"n_cols":7,"rows_kept":8,"cut":false,"hidden":false,"merged":[[0,0,0,1],[1,2,1,6]]}
["Berichtstermine",null,"2019-02-01","2019-04-01","2019-06-01","2019-07-01","2019-08-01"]
["Plan-PM","MS","Abschätzung der Personen-Monate zum Berichts-Termin"]
[162,"M1",166]
[186,"M2",195,205]
[210,"M3",210,210,210]
[145,"M4",148,156,162]
[122,"M5",122,132,144,138]
[135,"M6",132,134,144,142,143]