{"text_format":"1","workbook":"xlsx","n_sheets":2,"sheets":["Cover","Aktivitäten"],"not_rendered":{"charts":1,"images":0,"macros":1,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Cover","index":0,"n_rows":23,"n_cols":3,"rows_kept":23,"cut":false,"hidden":false,"merged":[]}
[]
[]
[null,"Excel + VBA "]
[null,"für Controller"]
[]
[]
[null,"Kapitel",9]
[null,"Thema","Strategisches Projekt-Controlling"]
[]
[null,"Inhalt","Gantt-Diagramm"]
[]
[null,null," "]
[]
[]
[]
[]
[]
[null,"Version","2.0"]
[null,"Autor","Harald Nahrstedt"]
[null,"Datum","2023-08-04"]
[]
[]
[null,"Springer Verlag"]

{"sheet":"Aktivitäten","index":1,"n_rows":10,"n_cols":4,"rows_kept":10,"cut":false,"hidden":false,"merged":[]}
["Aktivität","Starttermin","Dauer","Endtermin"]
[" 2 Materialbestellung","2019-03-01",3,{"$f":"B2+C2","v":"2019-03-04"}]
[" 3 Arbeitsplanung","2019-03-01",5,"2019-03-06"]
[" 4 Materialkosten",{"$f":"D2","v":"2019-03-04"},4,"2019-03-08"]
[" 5 Materiallieferung",{"$f":"D2","v":"2019-03-04"},7,"2019-03-11"]
[" 6 Personalschulung",{"$f":"D3","v":"2019-03-06"},4,"2019-03-10"]
[" 7 Lohnkosten",{"$f":"D3","v":"2019-03-06"},5,"2019-03-11"]
[" 8 Selbstkosten",{"$f":"D4","v":"2019-03-08"},5,"2019-03-13"]
[" 9 Fertigung",{"$f":"D5","v":"2019-03-11"},6,"2019-03-17"]
["10 Lieferung",{"$f":"D9","v":"2019-03-17"},1,"2019-03-18"]