{"text_format":"1","workbook":"xlsx","n_sheets":2,"sheets":["Cover","AgilePlanung"],"not_rendered":{"charts":1,"images":0,"macros":1,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Cover","index":0,"n_rows":23,"n_cols":3,"rows_kept":23,"cut":false,"hidden":false,"merged":[]}
[]
[]
[null,"Excel + VBA "]
[null,"für Controller"]
[]
[]
[null,"Kapitel",10]
[null,"Thema","Operatives Projekt-Controlling"]
[]
[null,"Inhalt","Agile Projekt-Planung"]
[]
[null,null," "]
[]
[]
[]
[]
[]
[null,"Version","2.0"]
[null,"Autor","Harald Nahrstedt"]
[null,"Datum","2023-08-04"]
[]
[]
[null,"Springer Verlag"]

{"sheet":"AgilePlanung","index":1,"n_rows":17,"n_cols":7,"rows_kept":17,"cut":false,"hidden":false,"merged":[]}
["Aufgaben","Beschreibung","Verantwortlich","Start","Ende","Dauer","Status"]
["Sprint 1",null,"AB",{"$f":"MIN(D3:D6)","v":"2019-09-02"},{"$f":"MAX(E3:E6)","v":"2019-09-23"},{"$f":"E2-D2","v":21},{"$f":"AVERAGE(G3:G6)","v":0.89999999999999991}]
["Merkmal 1.1",null,"CD","2019-09-02","2019-09-08",{"$f":"E3-D3","v":6},1]
["Merkmal 1.2",null,"CD","2019-09-08","2019-09-14",6,1]
["Merkmal 1.3",null,"EF","2019-09-09","2019-09-16",7,0.9]
["Merkmal  1.4",null,"EF","2019-09-12","2019-09-23",11,0.7]
["Sprint 2",null,"AB",{"$f":"MIN(D8:D10)","v":"2019-09-16"},{"$f":"MAX(E8:E10)","v":"2019-09-26"},10,{"$f":"AVERAGE(G8:G10)","v":0.23333333333333336}]
["Merkmal 2.1",null,"CD","2019-09-16","2019-09-20",{"$f":"E8-D8","v":4},0.2]
["Merkmal 2.2",null,"EF","2019-09-18","2019-09-23",{"$f":"E9-D9","v":5},0.35]
["Merkmal 2.3",null,"CD","2019-09-21","2019-09-26",5,0.15]
["Sprint 3",null,"AC",{"$f":"MIN(D12:D14)","v":"2019-09-26"},{"$f":"MAX(E12:E14)","v":"2019-10-06"},10,{"$f":"AVERAGE(G12:G14)","v":0.10000000000000002}]
["Merkmal 3.1",null,"CD","2019-09-26","2019-10-02",{"$f":"E12-D12","v":6},0.1]
["Merkmal 3.2",null,"DG","2019-09-30","2019-10-05",{"$f":"E13-D13","v":5},0.05]
["Merkmal 3.3",null,"DG","2019-10-02","2019-10-06",4,0.15]
["Sprint 4",null,"AC",{"$f":"MIN(D16:D17)","v":"2019-10-06"},{"$f":"MAX(E16:E17)","v":"2019-10-16"},10,{"$f":"AVERAGE(G16:G17)","v":0.125}]
["Merkmal 4.1",null,"DF","2019-10-06","2019-10-12",6,0.15]
["Merkmal 4.2",null,"DE","2019-10-08","2019-10-16",8,0.1]