{"text_format":"1","workbook":"xlsx","n_sheets":2,"sheets":["Cover","MTA"],"not_rendered":{"charts":1,"images":0,"macros":1,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Cover","index":0,"n_rows":23,"n_cols":3,"rows_kept":23,"cut":false,"hidden":false,"merged":[]}
[]
[]
[null,"Excel + VBA "]
[null,"für Controller"]
[]
[]
[null,"Kapitel",10]
[null,"Thema","Operatives Projekt-Controlling"]
[]
[null,"Inhalt","Meilenstein-Trend-Analyse"]
[]
[null,null," "]
[]
[]
[]
[]
[]
[null,"Version","2.0"]
[null,"Autor","Harald Nahrstedt"]
[null,"Datum","2023-08-04"]
[]
[]
[null,"Springer Verlag"]

{"sheet":"MTA","index":1,"n_rows":11,"n_cols":9,"rows_kept":11,"cut":false,"hidden":false,"merged":[[1,2,1,8],[0,0,0,1]]}
["Berichtstermine",null,"2019-02-01","2019-04-01","2019-06-01","2019-08-01","2019-10-01","2019-12-01","2020-02-01"]
["Plan-Termine","MS","Abschätzung der Ist-Termine zum Berichts-Termin"]
["2019-01-01","M1","2019-01-15"]
["2019-02-15","M2","2019-03-01","2019-03-10"]
["2019-04-01","M3","2019-04-10","2019-04-15","2019-05-01"]
["2019-05-15","M4","2019-05-30","2019-05-30","2019-06-30"]
["2019-06-01","M5","2019-06-20","2019-06-25","2019-06-20","2019-06-20"]
["2019-08-01","M6","2019-08-15","2019-08-25","2019-08-10","2019-08-15","2019-08-20"]
["2019-10-15","M7","2019-11-15","2019-11-20","2019-11-20","2019-11-25","2019-11-10"]
["2019-11-15","M8","2019-12-10","2019-12-15","2019-12-10","2019-12-15","2019-12-10","2019-12-15"]
["2019-12-31","M9","2020-01-15","2020-01-15","2020-01-10","2020-01-10","2020-01-05","2020-01-10","2020-02-01"]