{"text_format":"1","workbook":"xlsx","n_sheets":2,"sheets":["Cover","Netzplan"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Cover","index":0,"n_rows":23,"n_cols":3,"rows_kept":23,"cut":false,"hidden":false,"merged":[]}
[]
[]
[null,"Excel + VBA "]
[null,"für Controller"]
[]
[]
[null,"Kapitel",8]
[null,"Thema","Strategisches Projekt-Controlling"]
[]
[null,"Inhalt","Netzplan"]
[]
[null,null," "]
[]
[]
[]
[]
[]
[null,"Version","1.0"]
[null,"Autor","Harald Nahrstedt"]
[null,"Datum","2025-04-27"]
[]
[]
[null,"Springer Verlag"]

{"sheet":"Netzplan","index":1,"n_rows":11,"n_cols":10,"rows_kept":11,"cut":false,"hidden":false,"merged":[]}
["Nr","Aktivitäten","von ","nach","Dauer","FAZ","SAZ",null,"Formeln in Spalte F","Formeln in Spalte G"]
[1,"Start",null,"2/3",0,0,{"$f":"MIN(G4-E4,G3-E3)","v":5},null,null,"=MIN(G4-E4;G3-E3)"]
[2,"Materialbestellung",1,"4/5",3,{"$f":"F2+E3","v":3},{"$f":"MIN(G6-E6,G5-E5)","v":8},null,"=F2+E3","=MIN(G6-E6;G5-E5)"]
[3,"Arbeitsplanung",1,"6/7",5,{"$f":"F2+E4","v":5},{"$f":"MIN(G8-E8,G7-E7)","v":11},null,"=F2+E4","=MIN(G8-E8;G7-E7)"]
[4,"Materialkosten",2,8,4,{"$f":"F3+E5","v":7},{"$f":"G9-E9","v":16},null,"=F2+E5","=G9-E9"]
[5,"Materiallieferung",2,9,7,{"$f":"F3+E6","v":10},{"$f":"G10-E10","v":15},null,"=F2+E6","=G10-E10"]
[6,"Personalschulung",3,9,4,{"$f":"F4+E7","v":9},{"$f":"G10-E10","v":15},null,"=F2+E7","=G10-E10"]
[7,"Lohnkosten",3,8,5,{"$f":"F4+E8","v":10},{"$f":"G9-E9","v":16},null,"=F2+E8","=G9-E9"]
[8,"Selbstkosten","4/7",10,5,{"$f":"MAX(F5,F8)+E9","v":15},{"$f":"G11-E11","v":21},null,"=MAX(I5;I8)+H9","=G11-E11"]
[9,"Fertigung","5/6",10,6,{"$f":"MAX(F6,F7)+E10","v":16},{"$f":"G11-E11","v":21},null,"=MAX(I6;I7)+H10","=G11-E11"]
[10,"Lieferung","8/9",null,1,{"$f":"MAX(F9,F10)+E11","v":17},22,null,"=MAX(I9;I10)+H11"]