{"text_format":"1","workbook":"xlsx","n_sheets":2,"sheets":["Cover","Netzplan"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Cover","index":0,"n_rows":23,"n_cols":3,"rows_kept":23,"cut":false,"hidden":false,"merged":[]}
[]
[]
[]
[null,"Project + VBA "]
[]
[]
[null,"Kapitel",5]
[null,"Thema","Vorgänge"]
[]
[null,"Inhalt","Netzplan"]
[]
[null,null," "]
[]
[]
[]
[]
[]
[null,"Version","1.0"]
[null,"Autor","Harald Nahrstedt"]
[null,"Datum","2023-10-28"]
[]
[]
[null,"Springer Verlag"]

{"sheet":"Netzplan","index":1,"n_rows":11,"n_cols":5,"rows_kept":11,"cut":false,"hidden":false,"merged":[]}
["Nr","Aktivitäten","von ","nach","Dauer"]
[1,"Task1",null,"2/3",0]
[2,"Task2",1,"4/5",3]
[3,"Task3",1,"6/7",5]
[4,"Task4",2,8,4]
[5,"Task5",2,9,7]
[6,"Task6",3,9,4]
[7,"Task7",3,10,5]
[8,"Task8",4,10,5]
[9,"Task9","5/6",10,6]
[10,"Task10","7/8/9",null,1]